- Highway/Transport Improvement Works in and around Bridgwater     Friday 15 April 2016

|  | Parish/Town | Location |  | Scheme Description/ Purpose |  | Update | Start | Finish |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Complete |  |  |  |  |  |  |  |  |
| Somerset County Council | Bridgwater |  | Parkway |  | Resurfacing Works. | Complete |  |  |
| EDF Energy | Bridgwater |  | Bridgwater |  | Drainage remedial works in vicinity of Cannington Bypass junction/Rodway. Two way traffic lights will be in place. |  |  |  |
| Somerset County Council | Otterhampton |  | C182 |  | Resurfacing remedial works. |  |  |  |
| Somerset County Council | Wembdon crossing |  | Wembdon Road |  | Works to upgrade existing Pelican crossing to a Puffin crossing to increase space and improve safety. |  |  |  |
| Continuing |  |  |  |  |  |  |  |  |
| Somerset County Council (The Bridgwater Way) | North Petherton | Taunton Road |  | Junction widening, improving footway and cycleway, signing and lining works. Including installation of a toucan crossing between Stockmoor residential estate and Marsh lane. |  | Works on the cycle path north of the roundabout are complete except the installation of bollards and some lining works. the toucan crossing is complete and operational | Oct 2015 | March 2016 |
| Somerset County Council | Huntworth | Huntworth Roundabout |  | Improvement works to Huntworth Roundabout to increase capacity. |  | Works are continuing to make good progress at the roundabout in Bridgwater. Pedestrians have now been diverted onto the west side of the A38 utilising the new footway / cycleway as far as the south side of the roundabout. Works are now in progress to the north of the roundabout on both the central island and the carriageway is being widened on the eastern side on the approach to the roundabout. Works are progressing well on the central island and the link from the M5 roundabout which is being widened. Laying new road foundations will be taking place in some areas commencing on 25 April. Lanes are currently closed on each approach to provide safe working areas for the contractor and to reduce traffic speed around the junction. | 4 Jan | July 2016 |
| Private contractor | Bridgwater | Bower Lane |  | Drainage works associated with Bridgwater Hospital. |  | 3 way temporary traffic lights. | 29 March | April 24 |
| Environment Agency | Cannington | Cannington |  | Trial works underway prior to Cannington flood alleviation scheme commencing. |  | Works under two way traffic lights. | 12 April | 14 April |
| Future |  |  |  |  |  |  |  |  |
| Environment Agency | Cannington | Cannington |  |  | Cannington flood alleviation scheme. | Works under two way traffic lights. | May tbc | July tbc |
| Somerset County Council | C182 Cannington – Combwich cycleway | C182 |  |  | Widening of existing narrow footway to create a shared footway/cycleway stretching from Cannington to Combwich along the C182. The existing carriageway will also be widened to six and a half metres from its existing six metre width and part of the carriageway will be resurfaced, this will include drainage works to help against surface water collecting on the road. | Works under temporary traffic lights. | April/May tbc | Summer tbc |
| Somerset County Council | Bridgwater | Penel Orlieu |  |  | Resurfacing works. | One day closure of Penel Orlieu. | 15 May | 15 May |

EDF Energy updates supplied to Somerset County Council by EDF Energy.

Dates for Utilities schemes can be obtained from www.roadworks.org.

Utilities Companies have a statutory right to work on the network and dates above are subject to change as a result, especially in the event of emergency/ urgent works.

For more information on EDF Energy Schemes you can the visit Hinkley Point visitor centre, located in Angel Place Shopping Centre in Bridgwater.  Open 09.00 - 16.00 Monday to Friday. Alternatively you can call 0800 096 9650 or email hinkley-enquiries@edf-energy.com

For more information on Somerset County Council highways schemes please call Somerset Direct on 0300 123 2224 or email: generalenquiries@somerset.gov.uk